## Schedule
Address
Project Start Date: |  | 2025-11-24
Task ID | Task Name | Duration (days) | Pred Task ID | Pred Type (FS/SS) | Lag (days) | Start | Finish | Status
1 | Site cut & crossover gravel | 1 |  |  | 1 | 2026-04-20 | 2026-04-20 | Completed
2 | House setout | 1 | 1 | FS | 0 | 2026-04-21 | 2026-04-21 | Planning
3 | Underground plumbing | 3 | 6 | FS | 0 | 2026-04-24 | 2026-04-28 | Planning
4 | Foundation materials delivery | 1 | 3 | FS | 0 | 2026-04-29 | 2026-04-29 | Planning
5 | Piers exacavation | 1 | 2 | FS | 0 | 2026-04-22 | 2026-04-22 | Planning
6 | Piers concrete pour | 1 | 5 | FS | 0 | 2026-04-23 | 2026-04-23 | Planning
7 | Piers engineering inspection | 1 | 6 | SS | 0 | 2026-04-23 | 2026-04-23 | Planning
8 | 4 slab pour | 1 | 9 | FS | 0 | 2026-05-02 | 2026-05-02 | Planning
9 | 4 Slab prepare | 1 | 4 | FS | 1 | 2026-05-01 | 2026-05-01 | Planning
10 | 4 Termite | 1 | 9 | SS | 0 | 2026-05-01 | 2026-04-20 | Planning
11 | 4 engineering inspection | 1 | 9 | FS | -1 | 2026-05-01 | 2026-05-01 | Planning
12 | 4 termite under frames | 1 | 8 | SS | 1 | 2026-05-04 | 2026-05-04 | Planning
13 | 4 ground floor framing delivery | 1 | 77 | FS | 3 | 2026-05-08 | 2026-05-08 | Planning
14 | 4 ground floor framing | 14 | 13 | FS | 0 | 2026-05-11 | 2026-05-28 | Planning
15 |  | 0 |  | FS | 0 | 2025-11-24 | 2025-11-21 | Planning
16 |  | 0 |  | FS | 0 | 2025-11-24 | 2025-11-21 | Planning
17 | 4 midfloor materials delivery | 1 | 18 | SS | 0 | 2026-05-29 | 2026-05-29 | Planning
18 | 4 midfloor joists and nogging install | 1 | 14 | FS | 0 | 2026-05-29 | 2026-05-29 | Planning
19 | 4 midfloor flooring install | 1 | 17 | FS | 0 | 2026-06-01 | 2026-06-01 | Planning
20 | 4 upper framing&lower roof delivery | 1 | 19 | SS | 0 | 2026-06-01 | 2026-06-01 | Planning
21 | 4 upper framing install | 2 | 20 | FS | 0 | 2026-06-02 | 2026-06-03 | Planning
22 | 4 lower roof truss install | 2 | 21 | FS | 0 | 2026-06-04 | 2026-06-05 | Planning
23 | 4 lower roof edge protection ? | 1 | 22 | FS | 0 | 2026-06-08 | 2026-06-08 | Planning
24 | 4 lower roof install | 5 | 23 | FS | 0 | 2026-06-09 | 2026-06-15
25 | 4 scaffolding up | 2 | 24 | FS | 0 | 2026-06-16 | 2026-06-17
26 | 4 upper roof truss delivery | 1 | 25 | SS | 0 | 2026-06-16 | 2026-06-16
27 | 4 upper roof truss install | 2 | 26 | FS | 0 | 2026-06-17 | 2026-06-18
28 | 4 upper roof edge protection （not required?) | 0 | 27 | FS | 0 | 2026-06-19 | 2026-06-18
29 | 4 upper roof install | 14 | 28 | FS | 0 | 2026-06-19 | 2026-07-08
30 | 4 electrical roughin | 2 | 29 | FS | 0 | 2026-07-09 | 2026-07-10
31 | 4 AC roughin | 2 | 29 | FS | 0 | 2026-07-09 | 2026-07-10
32 | 4 plumbing roughin | 2 | 30 | FS | 0 | 2026-07-13 | 2026-07-14
33 | 4 wall wrap | 1 | 27 | FS | 0 | 2026-06-19 | 2026-06-19
34 | 4 framing inspection | 1 | 27 | FS | 0 | 2026-06-19 | 2026-06-19
35 | 4 windows delivery | 1 | 29 | FS | -1 | 2026-07-08 | 2026-07-08
36 | 4 entry doors delivery | 1 | 29 | FS | -1 | 2026-07-08 | 2026-07-08 |  | Entry door TBA
37 | 4 lockup labour | 1 | 29 | FS | 0 | 2026-07-09 | 2026-07-09
38 | 4 staircase supply&install | 1 | 29 | FS | 0 | 2026-07-09 | 2026-07-09
39 | 4 brick delivery | 1 | 32 | FS | -1 | 2026-07-14 | 2026-07-14
40 | 4 brick install | 7 | 39 | FS | 0 | 2026-07-15 | 2026-07-23
41 | 4 Staircase measure | 1 | 19 | FS | 0 | 2026-06-02 | 2026-06-02
42 | 4 cladding delivery | 1 | 40 | FS | -1 | 2026-07-23 | 2026-07-23
43 | 4 cladding install | 7 | 42 | FS | 0 | 2026-07-24 | 2026-08-03
44 | 4 termite under bricks | 1 | 40 | SS | 0 | 2026-07-15 | 2026-07-15
45 | 4 external painting | 7 | 43 | FS | 0 | 2026-08-04 | 2026-08-12
46 | 4 scaffolding down | 1 | 45 | FS | 0 | 2026-08-13 | 2026-08-13
47 | 4 plasterboard supply&install&set | 10 | 65 | FS | 0 | 2026-07-16 | 2026-07-29
48 | 4 internal painting | 10 | 63 | FS | 0 | 2026-08-03 | 2026-08-14
49 | 4 tiles delivery | 1 | 63 | FS | -1 | 2026-07-31 | 2026-07-31
50 | 4 waterproofing&tiling labour | 10 | 49 | FS | 0 | 2026-08-03 | 2026-08-14
51 | 4 cabinetry install | 5 | 48 | FS | 0 | 2026-08-17 | 2026-08-21
52 | 4 benchtop measure | 1 | 51 | SS | 3 | 2026-08-20 | 2026-08-20
53 | 4 benchtop instsall | 1 | 52 | FS | 2 | 2026-08-25 | 2026-08-25
54 | 4 garage door supply&install | 1 | 46 | FS | 0 | 2026-08-14 | 2026-08-14
55 | 4 garage door measure | 1 | 37 | FS | 0 | 2026-07-10 | 2026-07-10
56 | 4 plumbing fittings delivery | 1 | 51 | FS | -1 | 2026-08-21 | 2026-08-21
57 | 4 plumbing fitout | 5 | 56 | FS | 0 | 2026-08-24 | 2026-08-28
58 | 4 electrical fitout | 5 | 67 | FS | 0 | 2026-08-25 | 2026-08-31
59 | 4 AC fitout | 2 | 51 | FS | 0 | 2026-08-24 | 2026-08-25
60 | 4 flooring | 3 | 57 | FS | 0 | 2026-08-31 | 2026-09-02
61 | 4 glass balustrade | 1 | 60 | FS | 0 | 2026-09-03 | 2026-09-03
62 | 4 fixout materials delivery | 1 | 47 | FS | -1 | 2026-07-29 | 2026-07-29
63 | 4 fixout labour | 2 | 62 | FS | 0 | 2026-07-30 | 2026-07-31
64 | 4 ceiling batten | 1 | 29 | FS | 0 | 2026-07-09 | 2026-07-09
65 | 4 insulation | 1 | 32 | FS | 0 | 2026-07-15 | 2026-07-15
66 | 4 shower mixer delivery | 1 | 32 | SS | -1 | 2026-07-10 | 2026-07-10
67 | 4 appliance delivery | 1 | 51 | FS | 0 | 2026-08-24 | 2026-08-24
68 | 4 landscaping | 5 | 74 | FS | 0 | 2026-09-03 | 2026-09-09
69 | 4 showerscreen&mirror install | 2 | 57 | FS | 0 | 2026-08-31 | 2026-09-01
70 | 4 robe&shelving fitout | 2 | 48 | FS | 0 | 2026-08-17 | 2026-08-18
71 | 4 final fit | 1 | 57 | FS | 0 | 2026-08-31 | 2026-08-31
72 | 4 Final inspection | 1 | 61 | FS | 0 | 2026-09-04 | 2026-09-04
73 | 4 termite for driveway | 1 | 74 | SS | -1 | 2026-08-31 | 2026-08-31
74 | 4 driveway | 2 | 58 | FS | 0 | 2026-09-01 | 2026-09-02
75 | 4 silicone | 1 | 69 | FS | 0 | 2026-09-02 | 2026-09-02
76 | 4 House clean | 1 | 72 | FS | 0 | 2026-09-07 | 2026-09-07
77 |  | 1 | 8 | FS | 0 | 2026-05-04 | 2026-05-04
78 |  | 1 | 40 | SS | 0 | 2026-07-15 | 2026-07-15
79
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
[6 empty] | 45985 | 45982
Notes:
1) Enter the Project Start Date in C1. 2) For each task, fill Task ID, Task Name, Duration (working days). 3) For dependent tasks, fill Pred Task ID (the predecessor's Task ID), Pred Type (FS or SS), and Lag (days; can be 0, positive, or negative). 4) Start and Finish will calculate automatically using WORKDAY (weekends excluded).
Formulas:
Finish = IF([Start]="","",WORKDAY([Start],[Duration (days)]-1))
Finish = IF([Start]="","",WORKDAY([Start],[Duration (days), row below]-1))
Start = IF([Pred Task ID]="",C2,IF([Pred Type (FS/SS)]="FS",WORKDAY(INDEX($H:$H,MATCH([Pred Task ID],$A:$A,0)),[Lag (days)]+1),WORKDAY(INDEX($G:$G,MATCH([Pred Task ID],$A:$A,0)),[Lag (days)])))
Start = [Start, row below]+1

## Gantt
Gantt View (linked to Schedule) |  | 24-Nov | 25-Nov | 26-Nov | 27-Nov | 28-Nov | 29-Nov | 30-Nov | 1-Dec | 2-Dec | 3-Dec | 4-Dec | 5-Dec | 6-Dec | 7-Dec | 8-Dec | 9-Dec | 10-Dec | 11-Dec | 12-Dec | 13-Dec | 14-Dec | 15-Dec | 16-Dec | 17-Dec | 18-Dec | 19-Dec | 20-Dec | 21-Dec | 22-Dec | 23-Dec | 24-Dec | 25-Dec | 26-Dec | 27-Dec | 28-Dec | 29-Dec | 30-Dec | 31-Dec | 1-Jan | 2-Jan | 3-Jan | 4-Jan | 5-Jan | 6-Jan | 7-Jan | 8-Jan | 9-Jan | 10-Jan | 11-Jan | 12-Jan | 13-Jan | 14-Jan | 15-Jan | 16-Jan | 17-Jan | 18-Jan | 19-Jan | 20-Jan | 21-Jan | 22-Jan | 23-Jan | 24-Jan | 25-Jan | 26-Jan | 27-Jan | 28-Jan | 29-Jan | 30-Jan | 31-Jan | 1-Feb | 2-Feb | 3-Feb | 4-Feb | 5-Feb | 6-Feb | 7-Feb | 8-Feb | 9-Feb | 10-Feb | 11-Feb | 12-Feb | 13-Feb | 14-Feb | 15-Feb | 16-Feb | 17-Feb | 18-Feb | 19-Feb | 20-Feb | 21-Feb | 22-Feb | 23-Feb | 24-Feb | 25-Feb | 26-Feb | 27-Feb | 28-Feb | 1-Mar | 2-Mar | 3-Mar | 4-Mar | 5-Mar | 6-Mar | 7-Mar | 8-Mar | 9-Mar | 10-Mar | 11-Mar | 12-Mar | 13-Mar | 14-Mar | 15-Mar | 16-Mar | 17-Mar | 18-Mar | 19-Mar | 20-Mar | 21-Mar | 22-Mar | 23-Mar | 24-Mar | 25-Mar | 26-Mar | 27-Mar | 28-Mar | 29-Mar | 30-Mar | 31-Mar | 1-Apr | 2-Apr | 3-Apr | 4-Apr | 5-Apr | 6-Apr | 7-Apr | 8-Apr | 9-Apr | 10-Apr | 11-Apr | 12-Apr | 13-Apr | 14-Apr | 15-Apr | 16-Apr | 17-Apr | 18-Apr | 19-Apr | 20-Apr | 21-Apr | 22-Apr | 23-Apr | 24-Apr | 25-Apr | 26-Apr
Task ID | Task Name | 45985 | 45986 | 45987 | 45988 | 45989 | 45990 | 45991 | 45992 | 45993 | 45994 | 45995 | 45996 | 45997 | 45998 | 45999 | 46000 | 46001 | 46002 | 46003 | 46004 | 46005 | 46006 | 46007 | 46008 | 46009 | 46010 | 46011 | 46012 | 46013 | 46014 | 46015 | 46016 | 46017 | 46018 | 46019 | 46020 | 46021 | 46022 | 46023 | 46024 | 46025 | 46026 | 46027 | 46028 | 46029 | 46030 | 46031 | 46032 | 46033 | 46034 | 46035 | 46036 | 46037 | 46038 | 46039 | 46040 | 46041 | 46042 | 46043 | 46044 | 46045 | 46046 | 46047 | 46048 | 46049 | 46050 | 46051 | 46052 | 46053 | 46054 | 46055 | 46056 | 46057 | 46058 | 46059 | 46060 | 46061 | 46062 | 46063 | 46064 | 46065 | 46066 | 46067 | 46068 | 46069 | 46070 | 46071 | 46072 | 46073 | 46074 | 46075 | 46076 | 46077 | 46078 | 46079 | 46080 | 46081 | 46082 | 46083 | 46084 | 46085 | 46086 | 46087 | 46088 | 46089 | 46090 | 46091 | 46092 | 46093 | 46094 | 46095 | 46096 | 46097 | 46098 | 46099 | 46100 | 46101 | 46102 | 46103 | 46104 | 46105 | 46106 | 46107 | 46108 | 46109 | 46110 | 46111 | 46112 | 46113 | 46114 | 46115 | 46116 | 46117 | 46118 | 46119 | 46120 | 46121 | 46122 | 46123 | 46124 | 46125 | 46126 | 46127 | 46128 | 46129 | 46130 | 46131 | 46132 | 46133 | 46134 | 46135 | 46136 | 46137 | 46138
1 | Site cut & crossover gravel | bar: 20-Apr 46132
2 | House setout | bar: 21-Apr 46133
3 | Underground plumbing | bar: 24-Apr 46136 to 26-Apr 46138
4 | Foundation materials delivery
5 | Piers exacavation | bar: 22-Apr 46134
6 | Piers concrete pour | bar: 23-Apr 46135
7 | Piers engineering inspection | bar: 23-Apr 46135
8 | 4 slab pour
9 | 4 Slab prepare
10 | 4 Termite
11 | 4 engineering inspection
12 | 4 termite under frames
13 | 4 ground floor framing delivery
14 | 4 ground floor framing
15 | 0
16 | 0
17 | 4 midfloor materials delivery
18 | 4 midfloor joists and nogging install
19 | 4 midfloor flooring install
20 | 4 upper framing&lower roof delivery
21 | 4 upper framing install
22 | 4 lower roof truss install
23 | 4 lower roof edge protection ?
24 | 4 lower roof install
25 | 4 scaffolding up
26 | 4 upper roof truss delivery
27 | 4 upper roof truss install
28 | 4 upper roof edge protection （not required?)
29 | 4 upper roof install
30 | 4 electrical roughin
31 | 4 AC roughin
32 | 4 plumbing roughin
33 | 4 wall wrap
34 | 4 framing inspection
35 | 4 windows delivery
36 | 4 entry doors delivery
37 | 4 lockup labour
38 | 4 staircase supply&install
39 | 4 brick delivery
40 | 4 brick install
41 | 4 Staircase measure
42 | 4 cladding delivery
43 | 4 cladding install
44 | 4 termite under bricks
45 | 4 external painting
46 | 4 scaffolding down
47 | 4 plasterboard supply&install&set
48 | 4 internal painting
49 | 4 tiles delivery
50 | 4 waterproofing&tiling labour
51 | 4 cabinetry install
52 | 4 benchtop measure
53 | 4 benchtop instsall
54 | 4 garage door supply&install
55 | 4 garage door measure
56 | 4 plumbing fittings delivery
57 | 4 plumbing fitout
58 | 4 electrical fitout
59 | 4 AC fitout
60 | 4 flooring
61 | 4 glass balustrade
62 | 4 fixout materials delivery
63 | 4 fixout labour
64 | 4 ceiling batten
65 | 4 insulation
66 | 4 shower mixer delivery
67 | 4 appliance delivery
68 | 4 landscaping
69 | 4 showerscreen&mirror install
70 | 4 robe&shelving fitout
71 | 4 final fit
72 | 4 Final inspection
73 | 4 termite for driveway
74 | 4 driveway
75 | 4 silicone
76 | 4 House clean
77 | 0
78 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
79 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0
0 | 0